Table of Contents

Cover Page	1

CR-05 - Goals and Outcomes	3

CR-10 - Racial and Ethnic composition of families assisted	9

CR-15 - Resources and Investments 91.520(a)	10

CR-20 - Affordable Housing 91.520(b)	15

CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)	17

CR-30 - Public Housing 91.220(h); 91.320(j)	19

CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)	21

CR-40 - Monitoring 91.220 and 91.230	24

CR-45 - CDBG 91.520(c)	26

CR-50 - HOME 24 CFR 91.520(d)	27

CR-55 - HOPWA 91.520(e)	29

CR-58 – Section 3	30

CR-60 - ESG 91.520(g) (ESG Recipients only)	31

## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improve existing affordable housing stock | Affordable Housing | CDBG: $ / ESG: $500000 / Section 108: $ | Rental units rehabilitated | Household Housing Unit | 125 | 0 | 0.00% | 25 | 0 | 0.00% |
| Improve existing affordable housing stock | Affordable Housing | CDBG: $ / ESG: $500000 / Section 108: $ | Homeowner Housing Added | Household Housing Unit | 500 | 0 | 0.00% |  |  |  |
| Improve existing affordable housing stock | Affordable Housing | CDBG: $ / ESG: $500000 / Section 108: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 0 | 0 |  | 100 | 0 | 0.00% |
| Increase neighborhood sustainability | Non-Homeless Special Needs | CDBG: $ / Section 108: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1500 | 0 | 0.00% | 300 | 0 | 0.00% |
| Increase neighborhood sustainability | Non-Homeless Special Needs | CDBG: $ / Section 108: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1100 | 0 | 0.00% | 220 | 0 | 0.00% |
| Increase the supply of affordable rental housing | Affordable Housing | CDBG: $ / Section 108: $ | Rental units constructed | Household Housing Unit | 60 | 0 | 0.00% | 12 | 0 | 0.00% |
| Increase the supply of affordable rental housing | Affordable Housing | CDBG: $ / Section 108: $ | Rental units rehabilitated | Household Housing Unit | 60 | 0 | 0.00% | 12 | 0 | 0.00% |
| Program Administration | Admin and Planning for CDBG, HOME, HOPWA and ESG Programs | CDBG: $ / HOPWA: $ / HOME: $ | Other | Other | 5 | 0 | 0.00% | 1 | 0 | 0.00% |
| Provide assistance to households in crisis | Affordable Housing Homeless | ESG: $ / RUSH - ESG Disaster Relief Grant: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 425 | 0 | 0.00% | 85 | 0 | 0.00% |
| Provide assistance to households in crisis | Affordable Housing Homeless | ESG: $ / RUSH - ESG Disaster Relief Grant: $ | Homeless Person Overnight Shelter | Persons Assisted | 13500 | 0 | 0.00% | 2700 | 0 | 0.00% |
| Provide assistance to households in crisis | Affordable Housing Homeless | ESG: $ / RUSH - ESG Disaster Relief Grant: $ | Homelessness Prevention | Persons Assisted | 500 | 0 | 0.00% | 100 | 0 | 0.00% |
| Provide assistance to households in crisis | Affordable Housing Homeless | ESG: $ / RUSH - ESG Disaster Relief Grant: $ | Other | Other | 5 | 0 | 0.00% | 1 | 0 | 0.00% |
| Provide opportunities for homeownership | Affordable Housing | HOME: $ / Section 108: $ | Homeowner Housing Added | Household Housing Unit | 40 | 0 | 0.00% | 8 | 0 | 0.00% |
| Provide opportunities for homeownership | Affordable Housing | HOME: $ / Section 108: $ | Direct Financial Assistance to Homebuyers | Households Assisted | 575 | 0 | 0.00% | 125 | 0 | 0.00% |
| Provide programs to support persons with HIV/AIDS | Affordable Housing Homeless Non-Homeless Special Needs | HOPWA: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 550 | 0 | 0.00% | 110 | 0 | 0.00% |
| Provide programs to support persons with HIV/AIDS | Affordable Housing Homeless Non-Homeless Special Needs | HOPWA: $ | Homelessness Prevention | Persons Assisted | 1125 | 0 | 0.00% | 225 | 0 | 0.00% |
| Provide programs to support persons with HIV/AIDS | Affordable Housing Homeless Non-Homeless Special Needs | HOPWA: $ | Housing for Homeless added | Household Housing Unit | 0 | 0 |  | 8 | 0 | 0.00% |
| Provide programs to support persons with HIV/AIDS | Affordable Housing Homeless Non-Homeless Special Needs | HOPWA: $ | Housing for People with HIV/AIDS added | Household Housing Unit | 40 | 0 | 0.00% | 26 | 0 | 0.00% |
| Provide programs to support persons with HIV/AIDS | Affordable Housing Homeless Non-Homeless Special Needs | HOPWA: $ | HIV/AIDS Housing Operations | Household Housing Unit | 50 | 0 | 0.00% |  |  |  |
| Provide programs to support persons with HIV/AIDS | Affordable Housing Homeless Non-Homeless Special Needs | HOPWA: $ | Other | Other | 1740 | 0 | 0.00% | 348 | 0 | 0.00% |
| Provide temporary rental assistance | Homeless | HOME: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 300 | 0 | 0.00% | 60 | 0 | 0.00% |
| Repayment of the Section 108 Loan | Non-Housing Community Development | CDBG: $ | Other | Other | 5 | 0 | 0.00% | 1 | 0 | 0.00% |
| Support Economic Development | Non-Housing Community Development | Section 108: $ | Other | Other | 1 | 0 | 0.00% | 1 | 0 | 0.00% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

The City of Charlotte and its partners continue to prioritize the housing, community development, and safety needs of Charlotte’s most vulnerable residents as the focal point for federal and local funded programs. The City’s success in neighborhood revitalization is measured by increased homeownership; housing construction and rehabilitation, and targeted investments that remove economic barriers for vulnerable populations while improving neighborhoods.

In FY2025, CDBG fuding was directed toward three areas: Housing Rehabilitation, Down Payment Assistance, and Infrastructure Assistance. As the City of Charlotte continues to grow, a core principle of City programming remains the creation of communities where all residents, regardless of income level, have access to safe, affordable, and thriging places to live, work and play.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

| Describe the clients assisted (including the racial and/or ethnicity of clients assisted with ESG) |  |
| --- | --- |
|  | HESG |
| American Indian, Alaska Native, or Indigenous | 0 |
| Asian or Asian American | 0 |
| Black, African American, or African | 0 |
| Hispanic/Latina/e/o | 0 |
| Middle Eastern or North African | 0 |
| Native Hawaiian or Pacific Islander | 0 |
| White | 0 |
| Multiracial | 0 |
| Client doesn't know | 0 |
| Client prefers not to answer | 0 |
| Data not collected | 0 |
| Total | 0 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

Racial and ethnic demographic data for families and clients assisted during the program year is currently being collected and validated. The information presented in this draft CAPER is preliminary and will be updated to reflect final program year data prior to submission to HUD

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 5,741,754 |  |
| HOME | public - federal | 2,976,750 |  |
| HOPWA | public - federal | 3,858,201 |  |
| ESG | public - federal | 487,113 |  |
| RUSH - ESG Disaster Relief Grant | public - federal | 1,000,000 |  |
| Section 108 | public - federal | 25,000,000 | 0 |

Table 3 - Resources Made Available

Narrative

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| Citywide Low/Mod Eligible | 74 | 74 |  |
| Countywide Low/Mod Eligible | 1 | 1 |  |
| HOPWA Designated Service Area | 25 | 25 |  |

Table 4 – Identify the geographic distribution and location of investments

Narrative

The geographic distribution of investments reflects the City’s commitment to directing federal resources to eligible households and communities with identified housing, community development, and supportive service needs.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

The City of Charlotte continues to fund a local Housing Trust Fund to provide leverage for affordable housing projects. The City directly matches all HOME funds with the required local contribution at the outset of each project,ensuring compliance maximizing investment. The City has implemented a land disposition policy that requires all city-owned parcels to be reviewed for potential use as affordable housing prior to land disposal. Through this policy, several City parcels have been successfully dedicated to affordable housing development.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year |  |
| 2. Match contributed during current Federal fiscal year |  |
| 3 .Total match available for current Federal fiscal year (Line 1 plus Line 2) |  |
| 4. Match liability for current Federal fiscal year |  |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) |  |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at begin-ning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number |  |  |  |  |  |  |
| Dollar Amount |  |  |  |  |  |  |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number |  |  |  |  |  |  |
| Dollar Amount |  |  |  |  |  |  |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Number |  |  |  |
| Dollar Amount |  |  |  |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number |  |  |  |
| Dollar Amount |  |  |  |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number |  |  |  |  |  |  |
| Dollar Amount |  |  |  |  |  |  |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired |  |  |
| Businesses Displaced |  |  |
| Nonprofit Organizations Displaced |  |  |
| Households Temporarily Relocated, not Displaced |  |  |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number |  |  |  |  |  |  |
| Cost |  |  |  |  |  |  |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 342 | 0 |
| Number of Special-Needs households to be provided affordable housing units | 0 | 0 |
| Total | 342 | 0 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 60 | 0 |
| Number of households supported through The Production of New Units | 145 | 0 |
| Number of households supported through Rehab of Existing Units | 137 | 0 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| Total | 342 | 0 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

The City of Charlotte establishes goals in the Annual Action Plan to set targets for housing, community development, and supportive services. These goals represent the City’s intended direction and planned level of activity. Outcomes, as reported in the CAPER, reflect the measurable results achieved during the program year.

In FY2025 several external factors impacted the city’s ability to fully meet projected outcomes:

- Low housing stock , contractor shortageas limited the production of rental assistance units and housing rehabilitation projects.

- Rising interest rates and increased home sale prices reduced affordability.

Discuss how these outcomes will impact future annual action plans.

These outcomes provide insight into shaping future strategies. The City will continue to prioritize affoardable housing preservation and production as the focal point of its federal funding allocations.

A greater emphasis will be placed on preserving existing affordable housing through Acquistion Rehabilitation to offset limited supply. Policy tools such as the land disposition policy and zoning strategies will continue to be used to increase development opportunities. The city will also contune to expand the use of local Housing Trust Fund dollars to leverage federal funds and strengthen project feasibility.

While these outcomes demonstrate positive progress, the affordability and availability of housing for vulnerable households will remain a challenge for Charlotte as a rapidly growing city. The City will use these lessons to refine its future Annual Action Plans, ensuring resources are targeted to meet the greatest needs.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 0 | 0 |
| Low-income | 0 | 0 |
| Moderate-income | 0 | 0 |
| Total | 0 | 0 |

Table 13 – Number of Households Served

Narrative Information

Income-level data for households served through CDBG- and HOME-funded activities is currently being collected, reviewed, and validated. The figures reflected in this draft CAPER are placeholders and do not represent final program year accomplishments. Final data, including the number of extremely low-income, low-income, and moderate-income households served, will be updated prior to submission of the final CAPER to HUD.

During the program year, HUD funded activities assisted a toalt of TBD households through the CDBG and HOME programs. These outcomes demonstarate the City’s continued commitment to serving household across income levels, with an emphasis on Charlotte’s most vulenarble households

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs.

Charlotte-Mecklenburg continued to utilize the Coordinated Entry process to engage all persons who are homeless or at risk of homelessness to assess housing needs and connect with available resources in the community. The local Coordinated Entry process utilizes a standardized evaluation tool for both households who are homeless and at-risk of homelessness. The City, County, and local funds were utilized to increase Street Outreach activities to locate and engage unsheltered persons to connect with shelter options and move directly into housing, if available. Street Outreach Teams coordinate outreach activities utilizing the Communities Outreach Strategic Plan.

Addressing the emergency shelter and transitional housing needs of homeless persons.

The City partnered with three shelters providing services to homeless households. Roof Above provides emergency shelter to homeless men. The Salvation Army Center of Hope provides shelter to single women and families. Safe Alliance provides shelter to victims of domestic violence and sexual assault. Along with the emergency shelter organizations, several other non-profit housing partners provide transitional housing with wrap around services. Utilizing HOME, HOME-ARP, HOPWA, ESG, ESG-RUSH and locally funded, multiple organizations offered short and medium-term financial assistance and/or supportive services.  Efforts are being directed at Street Outreach activities to engage unsheltered individuals. In partnership with Mecklenburg  County and local providers , the City continued targeted unsheltered homelessness and homelessness prevention local initiatives.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs.

Charlotte-Mecklenburg‘s Coordinated Entry (CE) process assessed individuals who were homeless utilizing a standardized evaluation tool to assess and assist persons to become re-housed as quickly as possible, as well as, households at risk of/imminent risk or homelessness to assess/assist persons to maintain housing.  In addition to dedicated Coordination Entry staff, providers serving special populations completed assessments including Youth, Veterans, and Persons fleeing domestic violence, dating violence, sexual assault, and stalking. Agencies such as health providers, law enforcement agencies, and more traditional service providers worked together to meet client specific needs with a goal of self-sufficiency. Shelter providers continued to utilize diversion programs as part of the systematic responses to preventing homelessness and the need to enter the shelter system. Through the Charlotte-Mecklenburg A Home For All Strategic Framework, the community continued the work to reorient service provision around people’s progress on the housing continuum from homelessness and housing insecurity to housing stability including centralized information regarding available services and remaining supportive and present for people as they move along the housing continuum.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again.

This year TBD accessed one or more City-funded short- and medium-term financial assistance programs. This intentional use of funding (both financial assistance and case management services) is one of the community’s core strategies for housing stability. Street outreach, coordinated entry and diversion processes play key roles in ensuring households receive the needed housing and services for their individual needs. The community continued to participate in the Built for Zero Initiative which brings together a coalition of organizations that partner around this work and is succeeding in placing homeless Veterans in housing throughout the year.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

INLIVIAN, formerly the Charlotte Housing Authority (CHA), converted 3,284 Public Housing units to Project Based Voucher (PBV) funding through the Housing and Urban Development (HUD) Rental Assistance Demonstration (RAD) program in 2016 and 2017. INLIVIAN’s final public housing site, Dillehay Courts, was redeveloped in 2023.  The Gaston at North End, Phase I of the redevelopment of Dillehay Courts Apartments, is complete and encompasses 144 units featuring 1, 2, and 3 bedrooms. Phase I includes 51 PBV vouchers.  The second phase will include 100 PBV vouchers, maintaining the same number of subsidized units as the original Public Housing development.  Conversion to the RAD PBV platform allowed INLIVIAN to leverage public and private debt and equity to reinvest in the affordable housing stock while ensuring that units remain permanently affordable to low-income households. A key focus in addressing the needs of INLIVIAN’s portfolio in 2026 is for INLIVIAN to continue to act as a resource and community ally for INLIVIAN clientele who previously resided at Dillehay and the adjacent neighborhood community through the redevelopment phases.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership.

INLIVIAN has dedicated staff within its non-profit supportive services entity, CORE Programs, that work with an increasingly active Resident Advisory Council (RAC) to recruit, empower, and ensure residents are active in agency decision-making and community leadership prospects. Resident Advisory Council leaders meet monthly with INLIVIAN’s CEO and property management staff to discuss new ideas, plans, and/or community concerns.

In 2016, INLIVIAN launched its homeownership program, Destination Homeownership. The program empowers and assists qualified Housing Choice Voucher and Rental Assistance Demonstration (RAD)-Project Based Voucher (PBV) participants who are first-time buyers in the purchase of their version of the American Dream.

A total of 194 families have purchased a home as of December 2025.  Although the rising cost of homes in the Charlotte market has created challenges in assisting low-income families with homeownership opportunities, the Destination Homeownership program has been able to assist eight (8) families with the purchase of a home so far in 2026.  The homes that families were able to purchase included pre-existing and new-construction single-family homes and townhomes. Destination Homeownership families are empowered through homeownership education and counseling, and educational programming that includes workshops, individual counseling sessions, and credit and debt reduction services.

Actions taken to provide assistance to troubled PHAs

N/A

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i).

The City of Charlotte and Mecklenburg County employ various strategies and initiatives to improve economic opportunity for low-wealth residents. Most of these efforts are integrated into the goals, programs and policies of the City of Charlotte Housing & Neighborhood Services, the Mecklenburg County Department of Social Services, and INLIVIAN.

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

The City of Charlotte continues to identify limited affordable housing options for low- and very low-income households, limited housing opportunities for persons with special needs, and insufficient resources to quickly rehouse individuals and families experiencing homelessness as obstacles to meeting underserved needs.

During the reporting period, the City continued efforts to address these obstacles by providing funding to support the development and preservation of affordable housing, including housing serving vulnerable and special-needs populations. The City also continued to support housing assistance and services designed to help individuals and families experiencing homelessness or housing instability obtain and maintain stable housing.

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

The City of Charlotte, through funding from the U.S. Department of Housing and Urban Development’s Office of Lead Hazard Control and Healthy Homes, is actively reducing lead-based paint hazards in pre-1978 housing to protect children and families. The LeadSafe Charlotte Program combines rigorous home assessments and hazard abatement with comprehensive community outreach, focusing on families with children under six who are most at risk of lead poisoning.

During the 2025–2026 program year, the City successfully continued implementation of its Lead Hazard Reduction and Healthy Homes Program to improve the health and safety of low-income households with children under the age of six. Program activities focused on identifying and eliminating lead-based paint hazards, addressing healthy homes deficiencies, and providing education to residents on environmental health and safety. Throughout the reporting period, the program maintained an active pipeline with the completion of 30 housing units

In addition to lead hazard reduction activities, Healthy Homes interventions were incorporated into rehabilitation work where eligible. These activities included installation of smoke and carbon monoxide detectors, correction of electrical and trip hazards, moisture and ventilation improvements, pest management measures, and other interventions designed to reduce environmental health risks.

The program has continued to strengthen partnerships with local contractors, nonprofit organizations, such as Habitat for Humanity and Rebuilding Together Greater Charlotte, and healthcare providers to increase outreach efforts and identify eligible households. Educational materials and counseling were provided to participating families regarding lead poisoning prevention, routine maintenance practices, and healthy home behaviors.

Overall, the program remains on track to meet its grant objectives by increasing the number of lead-safe housing units, improving indoor environmental quality, and reducing childhood exposure to lead and other residential health hazards.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

- The City’s Office of Youth Opportunities promotes economic opportunity and positive youth development by connecting young people with paid work experiences, career exploration, mentorship, and skill-building opportunities that support future education, employment, and economic mobility.

- Mecklenburg County's Work First Program to help lift households receiving public assistance out of their poverty circumstances and into full-time employment.

- INLIVIAN’s Family Self-Sufficiency (FSS) Program supports families in achieving greater economic independence through individualized goal setting and supportive services, including education assistance, job training and preparation, employment assistance, financial education, life coaching, transportation and childcare assistance, and community referrals.

- The City, County, private businesses, and nonprofit organizations joined together to develop the 2020-2025 Housing and Homelessness Strategy. This effort facilitates the public and private sector coming together to address the full housing continuum, from street homelessness, upstream to households experiencing cost-burden.

- A Home For All 2.0 is a community-wide effort designed to focus on homelessness prevention, housing stability, affordable housing production, and services and resources for individuals and families experiencing homelessness.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

The City continued to enhance coordination among public and private housing and social service agencies through its participation in the Charlotte-Mecklenburg Continuum of Care (CoC). The City worked collaboratively with Mecklenburg County, nonprofit organizations, housing providers, and other community partners to coordinate resources and services for individuals and families experiencing or at risk of homelessness and those with special needs.

The City also continued to support A Home For All, Charlotte-Mecklenburg’s communitywide strategy to address homelessness and housing instability. Through these partnerships, the City supported efforts to strengthen homelessness prevention, housing stability, access to affordable housing, and connections to supportive services.

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

The City of Charlotte has established programs and resources to mitigate barriers to fair housing choice. The Charlotte Community Relations Committee focused on preventing discrimination in Charlotte-Mecklenburg. The Committee accepts formal complaints from any party who feels discrimination when they are renting, buying, or securing financing for any housing. The prohibitions specifically cover discrimination because of race, color, religion, national origin, gender, familial status or disability. The Committee also provides fair housing education and outreach services. Charlotte conducts yearly tests of multifamily housing complexes for fair housing compliance.

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

The City uses a multi-layered approach to ensure that housing strategy, short and long-term goals, program-specific regulations, and general state and federal statutes are followed. The planning process involves creating draft documents that are reviewed internally, reviewed by elected officials, and published for comment. Several public forums are conducted to explain the content and use of the plan document. The City Council approves all plans by vote.

Activities are designed to achieve the outcomes set forth in the plan and are conducted using multiple delivery methods such as City staff, sub-recipients, contractors, or other third parties such as land owners or developers. Staff follows federal, state, and local guidelines related to the selection of parties who may use federal dollars. Several City staff persons are assigned to monitor activities for compliance including contract monitors, a multifamily project manager, asset management, and a compliance team.

Responsible parties regularly report the status of each activity to ensure plan goals will be completed. At the end of each year, accomplishments are compared to goals to determine the status of planned activities and make any necessary adjustments to future activities. The City of Charlotte also monitors Davis Bacon, Section 3, Environmental and State Historic Preservation Office compliance to ensure projects comply with all applicable crosscutting requirements.

The City has adopted a Contract and Subrecipient Risk Framework, Analysis and Mitigation Strategy which details staff strategies to identify and mitigate risks, focus on third-party contracts for city programs, aligns City Finance policies and federal guidelines (2 CFR 200.332) for partner agency relationships, ensuring effective risk management, and improved outcomes for community initiatives.

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

The City of Charlotte provides citizens with reasonable notice and an opportunity to comment on the draft CAPER through a public notice. During the designated public comment period, the draft CAPER will be available on the City’s website https://www.charlottenc.gov/Streets-and-Neighborhoods/Housing  and at the City of Charlotte, 600 East Trade Street, Charlotte, NC, and INLIVIAN, 400 East Boulevard, Charlotte, NC 28203. A copy may also be mailed upon request.

Following the close of the public comment period, all comments received will be reviewed and considered prior to submission of the final CAPER to HUD. A summary of comments received, if any, will be included in the final report.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

The City's CDBG-funded programs were conducted as specified in the 2025 Action Plan. The programs achieved their intended outcomes.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants? No

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

N/A

## CR-50 - HOME 24 CFR 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in 24 CFR §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

The City of Charlotte is currently compiling the HOME assisted rental project inspection data for the reporting period. The final CAPER response will identify the projects requiring an on-site inspection during the program year,  the projects inspected, any compliance issues identified, and the status of corrective actions, if applicable.

For any required inspections that were not completed during the program year, the final response will identify the reason for the delay and the actions the City will take to address the outstanding inspection.

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 24 CFR 91.520(e) and 24 CFR 92.351(a)

The City of Charlotte continued to implement affirmative marketing practices and expand access to affordable housing throughout the 2025 reporting period. Through the City’s down payment assistance program, HOME funds were used to reduce barriers to homeownership by providing down payment and closing cost assistance, making market-rate units affordable to low- and moderate-income households. The City, in partnership with DreamKey Partners, conducts outreach and training with real estate agents and first loan providers to ensure the program is accessible and widely utilized. Targeted outreach is directed toward lenders with community based loan programs frequently accessed by underrepresented homebuyers.

In addition, HOME funds were used through nonprofit development partners to produce a variety of affordable housing options. Nonprofit and development partner are required to comply with the  City’s affirmative marketing requirements for their projects, ensuring that all housing opportunities are marketed broadly and equitably, and that diverse populations have equal access to housing resources.

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics.

The City of Charlotte is currently reviewing IDIS reports to determine the amount of program income received and expended during the FY2025–2026 program year. The final CAPER will identify the amount and use of HOME and CDBG program income, including the number of projects supported and applicable owner and tenant characteristics

Describe other actions taken to foster and maintain affordable housing. 24 CFR 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 24 CFR 91.320(j) N/A

## CR-55 - HOPWA 91.520(e)

Identify the number of individuals assisted and the types of assistance provided

Table for report on the one-year goals for the number of households provided housing through the use of HOPWA activities for: short-term rent, mortgage, and utility assistance payments to prevent homelessness of the individual or family; tenant-based rental assistance; and units provided in housing facilities developed, leased, or operated with HOPWA funds.

| Number of Households Served Through: | One-year Goal | Actual |
| --- | --- | --- |
| Short-term rent, mortgage, and utility assistance payments | 225 |  |
| Tenant-based rental assistance | 83 |  |
| Units provided in transitional housing facilities developed, leased, or operated with HOPWA funds | 18 |  |
| Units provided in permanent housing facilities developed, leased, or operated with HOPWA funds | 0 |  |
| Total |  |  |

Table 14 – HOPWA Number of Households Served

Narrative

The City of Charlotte continued to administer HOPWA funding through community partners to provide housing assistance and supportive services to eligible individuals and households living with HIV/AIDS. HOPWA-funded activities included Short-Term Rent, Mortgage, and Utility (STRMU) assistance, Tenant-Based Rental Assistance (TBRA), and transitional housing assistance.

These activities are designed to prevent homelessness, promote housing stability, and assist eligible households in maintaining or obtaining safe and stable housing. Final household and beneficiary data are currently being compiled and will be incorporated into the final CAPER.

## CR-58 – Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Total Number of Activities | 2 | 0 | 0 | 0 | 0 |
| Total Labor Hours | 15,505.11 |  |  |  |  |
| Total Section 3 Worker Hours |  |  |  |  |  |
| Total Targeted Section 3 Worker Hours |  |  |  |  |  |

Table 15 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers |  |  |  |  |  |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. |  |  |  |  |  |
| Direct, on-the job training (including apprenticeships). |  |  |  |  |  |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. |  |  |  |  |  |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). |  |  |  |  |  |
| Outreach efforts to identify and secure bids from Section 3 business concerns. |  |  |  |  |  |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. |  |  |  |  |  |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with assistance in seeking employment including: drafting resumes,preparing for interviews, finding job opportunities, connecting residents to job placement services. |  |  |  |  |  |
| Held one or more job fairs. |  |  |  |  |  |
| Provided or connected residents with supportive services that can provide direct services or referrals. |  |  |  |  |  |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. |  |  |  |  |  |
| Assisted residents with finding child care. |  |  |  |  |  |
| Assisted residents to apply for, or attend community college or a four year educational institution. |  |  |  |  |  |
| Assisted residents to apply for, or attend vocational/technical training. |  |  |  |  |  |
| Assisted residents to obtain financial literacy training and/or coaching. |  |  |  |  |  |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with training on computer use or online technologies. |  |  |  |  |  |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. |  |  |  |  |  |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. |  |  |  |  |  |
| Other. | X |  |  |  |  |

Table 16 – Qualitative Efforts - Number of Activities by Program

Narrative

During FY2025 the City of Charlotte’s partners continued efforts to support compliance with Section 3 requirements for all applicable federally funded projects. Partners provided Section 3 compliance packets to general contractors outlining program requirements, including guidance on new hire reporting, resident verification, required documentation, and qualifications for Section 3 business concerns.

Partners also provided access to additional Section 3 information and resources through contractor outreach materials, including QR codes and online resources. Applicable income limits were updated to coincide with  HUD’s annual published income limits.

## CR-60 - ESG 91.520(g) (ESG Recipients only)

ESG Supplement to the CAPER in e-snaps

For Paperwork Reduction Act

1. Recipient Information—All Recipients Complete

Basic Grant Information

| Recipient Name | Charlotte |
| --- | --- |

| Organizational DUNS Number | 071064166 |
| --- | --- |

| UEI |  |
| --- | --- |

| EIN/TIN Number | 521333483 |
| --- | --- |

| Indentify the Field Office | GREENSBORO |
| --- | --- |

| Identify CoC(s) in which the recipient or subrecipient(s) will provide ESG assistance |  |
| --- | --- |

ESG Contact Name

| Prefix | Mr |
| --- | --- |

| First Name | Marcus |
| --- | --- |

| Middle Name | D |
| --- | --- |

| Last Name | Jones |
| --- | --- |

| Suffix |  |
| --- | --- |

| Title | City Manager |
| --- | --- |

ESG Contact Address

| Street Address 1 | 600 E. Trade Street |
| --- | --- |

| Street Address 2 |  |
| --- | --- |

| City | Charlotte |
| --- | --- |

| State | NC |
| --- | --- |

| ZIP Code | - |
| --- | --- |

| Phone Number | 7043362241 |
| --- | --- |

| Extension |  |
| --- | --- |

| Fax Number |  |
| --- | --- |

| Email Address | marcus.jones@charlotte.gov |
| --- | --- |

ESG Secondary Contact

| Prefix | Mr |
| --- | --- |

| First Name | Warren |
| --- | --- |

| Last Name | Wooten |
| --- | --- |

| Suffix |  |
| --- | --- |

| Title | HNS Assistant Director Housing |
| --- | --- |

| Phone Number | 7043362489 |
| --- | --- |

| Extension |  |
| --- | --- |

| Email Address | warren.wooten@charlottenc.gov |
| --- | --- |

2. Reporting Period—All Recipients Complete

| Program Year Start Date | 07/01/2025 |
| --- | --- |

| Program Year End Date | 06/30/2026 |
| --- | --- |

3a. Subrecipient Form – Complete one form for each subrecipient

Subrecipient or Contractor Name

City

State

Zip Code

DUNS Number

UEI

Is subrecipient a vistim services provider

Subrecipient Organization Type

ESG Subgrant or Contract Award Amount